## Checklist
# | Task | Category | Status | Owner | Due | Notes
1 | Website live (Letters, Books, About, Support, Privacy, Terms) | Build | Done | Ian |  | Deployed to GitHub Pages
2 | Email sign-up flow | Build | Done | Ian
3 | Bookshop + donation buttons wired (one config) | Store | Done | Ian |  | assets/store.js controls all buttons
4 | Graceful 'soon' state until links exist | Store | Done | Ian
5 | Seller chosen: Payhip | Decision | Done | Ian/Yael |  | Stripe + auto-delivery, no inventory
6 | Setup + delivery notes (STORE.md) | Docs | Done | Ian
7 | Preview / admin walkthrough page | Docs | Done | Ian |  | https://tradian.github.io/yaelsletters/store-preview.html
8 | Create Payhip account + connect Stripe | Store | Open | Yael |  | payhip.com — Settings → Payments
9 | Upload 'Letters from the Hill' ebook + price | Store | Open | Yael |  | Add Product → Digital
10 | Upload 'Before the Rooster' ebook + price | Store | Open | Yael
11 | Send the two Payhip buy links to Ian | Store | Open | Yael |  | Then buttons go live
12 | Paste links into store.js → buttons live | Store | Open | Ian |  | Waiting on task 11
13 | Decide on paper copies (print-on-demand) or skip | Decision | Open | Yael |  | Lulu / Amazon KDP if yes
14 | Deliver to already-presold buyers | Store | Open | Yael/Ian |  | Free coupon OR email the file
15 | Donations: Buy Me a Coffee page | Donations | Parked | Yael |  | Switch on when ready
16 | Optional Stripe donation link | Donations | Parked | Yael |  | 'Give another way' button

## Follow-ups
Date raised | Topic | Waiting on | Next action | Owner | Status | Notes
| Payhip setup | Yael | Create account + upload 2 ebooks | Yael | Open
| Buy links | Yael | Send both Payhip links to Ian | Yael | Open
| Paper copies | Yael | Decide: print-on-demand or skip | Yael | Open
| Presold delivery | Yael | Pick method (coupon vs email) | Yael | Open
| Donations | Yael | Confirm if/when to switch on BMC | Yael | Parked

## Links & Logins
What | Where / URL | Notes
Live website | https://tradian.github.io/yaelsletters/
Preview / admin walkthrough | https://tradian.github.io/yaelsletters/store-preview.html | Unlisted — share the link only
Payhip dashboard | https://payhip.com/ | Yael's day-to-day admin
Stripe dashboard | https://dashboard.stripe.com/ | Where the money lands
'Letters from the Hill' buy link |  | Paste here when created
'Before the Rooster' buy link |  | Paste here when created
Buy Me a Coffee page |  | Parked for now
Stripe donation link (optional) |  | Parked for now

## Assets to gather
Asset | Where it goes on the site | Format / spec | Received? | Notes
'Letters from the Hill' ebook file | Uploaded to Payhip (sold + delivered) | PDF or EPUB | No | The actual book
'Before the Rooster' ebook file | Uploaded to Payhip (sold + delivered) | PDF or EPUB | No
'Letters from the Hill' cover art | assets/covers/letters-from-the-hill.jpg | Portrait ~448x624px (2x), JPEG/WebP | No | Drops in automatically
'Before the Rooster' cover art | assets/covers/before-the-rooster.jpg | Portrait ~448x624px (2x), JPEG/WebP | No | Drops in automatically
Book blurb — Letters from the Hill | Book page + Payhip description | A paragraph of text | No
Book blurb — Before the Rooster | Book page + Payhip description | A paragraph of text | No
Prices (per book) | store.js + Payhip | e.g. $4.99 | No
Photo of Yael | About page | Landscape or portrait, good res | No
Short bio / 'about Yael' | About page | A few sentences | No
Reader notes / endorsements | Books or home (optional feature) | Short quotes + names | No
Logo / wordmark | Site branding / favicon | PNG/SVG, transparent | No | Optional
Facebook / contact links | Footer links | URLs | No